## Sheet1
SL | Modules | Module Status | Assigned- Back End | Status | Work Allocated Date | Expected Work Completion Date | Comments | Assigned- Front End | Status | Work Allocated Date | Expected Work Completion Date | Comments | Test Status | Faisal Comments
1 | Company Master | Completed | Shalik | Completed |  |  |  | Ashik | Completed
2 | Branch Master | Completed | Shalik | Completed |  |  |  | Ashik | Completed
3 | User | Completed | Shalik | Completed |  |  |  | Ashik | Completed
4 | User Group Master | Partailly | Shalik | Completed |  |  |  | Ashik | Started | 2024-03-25 | 3/27/2024
5 | Department | Completed | Shalik | Completed |  |  |  | Ashik | Completed
6 | Designation | Completed | Shalik | Completed |  |  |  | Ashik | Completed
7 | Category | Completed | Shalik | Completed |  |  |  | Ashik | Completed
8 | Employee Master | Completed | Shalik | Completed |  |  |  | Ashik | Completed
9 | Document Management | Completed | Shalik | Completed |  |  |  | Ashik | Completed
10 | ESS | Completed | Shalik | Completed |  |  |  | Ashik | Completed
11 | Employee Profile Dashboard | Not Started | Not Assigned | Not Assigned |  |  |  | Not Assigned | Not Started
12 | Dashboard -Employee Document Expiry Alers | Partailly | Shalik | Completed |  |  |  | Not Assigned | Not Started
13 | Employee Master Import | Partailly | Subina | Completed |  |  |  | Not Assigned | Not Started
14 | Employee Report | Not Started | Not Assigned | Not Assigned |  |  |  | Not Assigned | Not Started
15 | Schema Development | Partailly | Shalik | Started | 2024-03-25 |  |  | Not Assigned | Not Started
16 | UDF in Employee Master | Partailly | Subina | Started | 2024-03-25 |  |  | Not Assigned | Not Started